INTERNAL MANAGEMENT COMMUNICATION

# Business Memo

Decision and execution note

| TO | Executive Committee and Business Unit Heads |
| --- | --- |
| FROM | Marcus Lee, Chief Operating Officer |
| DATE | 7 October 2026 |
| SUBJECT | Operating Model Reset: Simplifying Delivery and Decision Rights |
| CLASSIFICATION | Internal - Management |

# Purpose

This memo confirms the operating-model changes approved by the Executive Committee on 5 October. The objective is to reduce hand-offs, clarify accountability, and improve the speed with which priority client commitments move from decision to delivery.

Decision Effective 1 November 2026, accountability for delivery will move to five end-to-end value streams. Each value stream will own demand shaping, prioritisation, engineering delivery, operational readiness and benefit tracking for its scope.

# What is changing

1. Five value streams

Client Onboarding; Markets & Confirmations; Payments & Treasury; Data & Regulatory; Enterprise Platforms.

2. One accountable executive

Each stream will have one Executive Sponsor and one Value Stream Lead with authority over priorities, capacity and delivery trade-offs.

3. Fewer governance layers

Project-level steering forums will be consolidated. Material risk, regulatory commitments and investment exceptions will continue to receive independent review.

4. Persistent product teams

Core capabilities will be staffed as enduring teams rather than repeatedly assembled project squads.

# Why now

Across the last two quarters, 37% of priority initiatives experienced delay attributable primarily to cross-team dependencies or unclear decision ownership.

Technology and operations teams are maintaining overlapping governance artefacts for the same outcomes.

Client commitments increasingly span product, data, engineering and operations; our current structure optimises functions more effectively than end-to-end outcomes.

EXECUTION

# Implementation plan

| WHEN | MILESTONE | OWNER | EVIDENCE OF COMPLETION |
| --- | --- | --- | --- |
| 14 Oct | Confirm value-stream charters | COO + Sponsors | Approved scope and decision rights |
| 21 Oct | Map people and in-flight work | BU Leads + HR | Named teams and transition risks |
| 28 Oct | Baseline service and delivery metrics | CIO + Operations | Baseline dashboard published |
| 1 Nov | New model goes live | All Sponsors | Governance and backlog ownership active |
| 30 Nov | 30-day health check | Transformation Office | Issues and corrective actions agreed |

# Non-negotiables

No reduction in independent risk, compliance or production-readiness controls.

Client and regulatory deadlines remain binding during transition.

Every service must retain a named business owner and technology owner.

Exceptions requiring more than five working days to resolve must be escalated to the relevant Executive Sponsor.

# Measures we will use

| ≤ 5 days DECISION LEAD TIME | ≥ 85% ON-TIME DELIVERY | −25% HAND-OFFS | ≥ 99.9% TIER-1 AVAILABILITY |
| --- | --- | --- | --- |

# Required action

Business Unit Heads should nominate their transition lead by 10 October and complete the attached value-stream mapping template by 17 October. Questions that affect more than one business unit should be raised through the Transformation Office so that a single answer can be published for all teams.

Communication principle Frame this as an accountability and flow redesign. Be clear on decisions, controls and success measures.